## Slide 1
NOT SCHEDULED

## Slide 2
2
AQ Upgrades to Emissions/Chemistry (Phase II)
Project Status as of 010/23/11
Issues/Risks
Finances
Scheduling
Project Information and Highlights
Associated Costs:
Funding Sources: EMC Base: T2O 4 Man-months
NCO Base: 2 man-months for implementation, 1 man-month annually for maintenance
Management Attention Required | Potential Management Attention Needed | On Target
G
R
Y
G
Lead: Jeff McQueen, EMC, Jianping Huang, Chris Magee, NCO
Scope:
Upgrade CMAQ to version 4.7 with improved chemistry mechanisms & vertical transport.
Upgrade Emissions with 2011 base year estimates.
Upgrade lateral boundary conditions.
Improved coupling between land and atmosphere
Inclusion of upgraded AERO-4 aerosol mechanism (note PM products will still be developmental).
Include wild fire smoke emissions
Expected Benefits:
Expansion of the AQFS whereby the AQM is incrementally improved through improved chemistry and physics and the overall forecast skill is raised.
Improved vertical transport, expanded coverage, emissions, unified script for all regional runs.
Milestone (NCEP) | Date | Status
EMC testing complete/ EMC CCB approval | 01/06/2012 | 
Final RFC submitted to NCO | 01/13/2012 | 
Technical Information Notice Issued | 03/19/2012 | 
Initial Test Complete | 01/27/2012 | 
CCB approve parallel data feed | 2/01/2012 | 
IT testing begins | 01/30/2012 | 
IT testing ends | 02/13/2012 | 
Parallel testing begun in NCO | 02/14/2012 | 
Real-Time Evaluation Ends | 03/13/2012 | 
Management Briefing | 03/20/2012 | 
Implementation | 03/27/2012 | 
Issues: Based on EMC priority and NCO resource availability, scheduling is not possible at this time
Risks:.
Mitigation:
G
G
G
Not currently scheduled
Notes: 2

## Slide 3
Not currently scheduled
Lead: Jeff McQueen, Geoff Manikin, Barbara Stunder, ARL,
Chris Magee, NCO
Scope:
All HYSPLIT applications
  All libraries and executables updated
  Vertical mass distribution, grib output files
  Higher resolution graphics
  Upgrade to current Google Earth & GIS capabilities
Regional Specialized Met Center
  Plume time of arrival, particle output, high res. graphics
  Option to use 1 hrly NAM forecasts
  Additional radionuclides
Smoke
  4 km Hawaii wild fire smoke dispersion
Expected Benefits:
Meet ICAO, FAA, WMO-RSMC & NAQFC requirements.
Improved unified system for all HYSPLIT applications
NAQFC : Upgrade of HYSPLIT Dispersion
Project Status as of 010/23/11
Issues/Risks
Issues:
Major upgrade w/ all codes and libraries updated
Risks:
Delay implementation of capabilities
Mitigation:..
Detailed testing for all applications underway
Finances
Scheduling
Project Information and Highlights
Associated Costs:
Funding Sources: EMC Base: T2O 4 Man-months
NCO Base: 2 man-months for implementation, 1 man-month annually for maintenance
Management Attention Required | Potential Management Attention Needed | On Target
G
R
G
G
G
Milestone (NCEP) | Date | Status
EMC testing complete/ EMC CCB approval | 10/18/2011 | 
Final RFC submitted to NCO | 10/25/2011 | 
Technical Information Notice Issued | 01/18/2012 | 
Initial Test Complete | 11/08/2011 | 
CCB approve parallel data feed | 11/14/2011 | 
IT testing begins | 11/09/2011 | 
IT testing ends | 11/22/2011 | 
Parallel testing begun in NCO | 11/28/2011 | 
Real-Time Evaluation Ends | 01/09/2012 | 
Management Briefing | 01/17/2012 | 
Implementation | 01/24/2012 | 
Y
G

## Slide 4: Not Currently Scheduled Implement as Resources Permit
Current Backlog
  Sea ice concentration using AMSR-E
  RTGSST HighRes background fields update (NQ)
  Sea ice concentration w/F15 in analysis
  Gridded MOS Guidance for Puerto Rico (P,D)
  Gridded LAMP Winds, Sky Cover, Obstruction to Vision, Probability of Precipitation Occurring
  RTOFS Atlantic
  Adding SLOSH water levels to hurricane wave model.
  Sea ice drift model service upgrade (NQ)
  Gridded LAMP and MOS convective forecasts
  AQ Upgrades to Emissions/Chemistry
  Grid-To-Grid Verification (NQ)
  NAQFC : Upgrade of HYSPLIT Dispersion
  RTMA Upgrade V2.0.0
  Weekly IO SST analysis (NQ)
  RTOFS Global V1.1.0
  RTOFS Global V1.2.0